## Hours Details
Client: |  | System Source |  |  |  |  | Week Ending: |  | 2023-01-14
|  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Total
Task Descriptions | Subject Area | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14
Continue working for the permission and client loading while login and select client. | Inventory Api & Inventory Website | 2023-01-09: 3 | 3
Continue working for the DB Changes to map with code. | Inventory Api & Inventory Website | 2023-01-09: 3 | 3
Deploy the changes as modified all changes. |  | 2023-01-09: 2 | 2
0
0
Meeting Call | Programmer Meeting Call | 2023-01-10: 2 | 2
As discussed in the meeting start changing the code to follow the order status in order and orderitem table. | InvHDRequestApi & Inventory Website | 2023-01-10: 6 | 6
0
0
0
As discussed in meeting calll, start working for the Maintenance and cleaning request api call. | InvHDRequestApi & Inventory Website | 2023-01-11: 8 | 8
0
0
0
0
Continue working for the Maintenance and cleaning request api call to make generic type of code. | InvHDRequestApi & Inventory Website | 2023-01-12: 5 | 5
IT Integration Meeting Call. | IT Integration Meeting | 2023-01-12: 0.5 | 0.5
Continue working for the Maintenance and cleaning request api call to make generic type of code. | InvHDRequestApi & Inventory Website | 2023-01-12: 2.5 | 2.5
0
0
0
0
having some issue to make generic type of code for the maintenance and cleaning request. | InvHDRequestApi & Inventory Website | 2023-01-13: 8 | 8
0
0
0
0
|  | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 40
Approved By: