## Hours Details
Client: |  | System Source |  |  |  |  | Week Ending: |  | 2022-08-13
|  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Total
Task Descriptions | Subject Area | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13
Start Code mapping for the download and upload aws s3 bucket api | Inventory test site and Api | 2022-08-08: 4 | 4
Start testing for the mapping to display images using api call, but figure out the performance issue, so try to find root cause of performance issue. | Inventory test site and Api, s3 upload download api | 2022-08-08: 4 | 4
0
Meeting Call | Programmer Meeting Call | 2022-08-09: 2.5 | 2.5
Try to implement the best way to get aws credential only first call of upload download api using singleton pattern. | Upload , Download S3 bucket api | 2022-08-09: 5.5 | 5.5
0
0
0
Continue implementing the best way to get aws credential only first call of upload download api using singleton pattern. | Upload , Download S3 bucket api | 2022-08-10: 4 | 4
Start implementing the global creation of Http Client Object to call upload and download aws s3 api to reduce the loading performance of redirection of another api call. | Inventory Api | 2022-08-10: 4 | 4
0
0
0
Continue implementing the global creation of Http Client Object to call upload and download aws s3 api to reduce the loading performance of redirection of another api call. | Inventory test site and Api | 2022-08-11: 3 | 3
Meeting Call | IT Meeting Call | 2022-08-11: 2 | 2
Start implementing the image download from typescript and bind to image url. | Inventory test site and Api | 2022-08-11: 3 | 3
0
0
0
0
Continue implementing and testing the image download from typescript and bind to image url. | Inventory test site and Api | 2022-08-12: 8 | 8
0
0
0
0
|  | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 40
Approved By: