## Hours Details
Client: |  | System Source |  |  |  |  | Week Ending: |  | 2022-06-04
|  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Total
Task Descriptions | Subject Area | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04
0
0
0
Meeting Call | Programmer Meeting Call | 2022-05-31: 3 | 3
Start work for UI Changes after demo in meeting. | Inventory test site and Api | 2022-05-31: 5 | 5
0
0
0
Working for the check out flow cross verification while adding to cart and before request order. | Inventory test site and Api | 2022-06-01: 8 | 8
0
0
0
0
start working for the Warranty Disply screen to shows Inventory Item Level Inventory. | Inventory test site and Api | 2022-06-02: 5 | 5
Meeting Call | IT Meeting | 2022-06-02: 0.5 | 0.5
Start working for the sch integration api mapping same as help desk site. | sch integration api | 2022-06-02: 2 | 2
Continue working for the Warranty Disply screen to shows Inventory Item Level Inventory. | Inventory test site and Api | [7 empty] | 1 | bar: 2022-06-02
0
0
0
Working for the dev environment set up for the sch integration api on charon-3 server. | sch integration api dev | 2022-06-03: 4 | 4
point production sch integration api to https and made accordingly. | sch integration api prod | 2022-06-03: 2 | 2
Continue working for the warranty display screen to shows inventory item level inventory. | Inventory test site and Api | 2022-06-03: 1.5 | 1.5
0
0
|  | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 32
Approved By: