## Hours Details
Client: |  | System Source |  |  |  |  | Week Ending: |  | 2022-06-25
|  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Total
Task Descriptions | Subject Area | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25
Continue working for the UI Changes of the small screen of Add to cart page. | Inventory test site and Api | 2022-06-20: 4 | 4
Start deployment process on charon-4 & charon-3. | Deployment process | 2022-06-20: 4 | 4
0
Meeting Call | Programmer Meeting | 2022-06-21: 3 | 3
fix the issue to load inventory while deployed to server. | Deployment process issue | 2022-06-21: 2 | 2
After Fix issue deploy the new version and testing. While testing charon-3 inventory WebApi is not working. So, trying to fix the issue. | Fix issue and deploy to server | 2022-06-21: 3 | 3
0
0
Start working for the changes while demo in programmer meeting call. | Inventory test site and Api | 2022-06-22: 7 | 7
Meeting call with rednight to workout for the upload and download image/files to s3 bucket issue after change the Access and screte key. | s3 bucket issue | [7 empty] | 1 | bar: 2022-06-22
0
0
0
Test version site have again issue to load data if initial load. | Inventory test site and Api server issue | 2022-06-23: 2 | 2
Continue working for the SpaceType load belong to specific client if data availble for that. | Inventory test site and Api server | 2022-06-23: 2 | 2
IT Itegration Meeting | Meeting Call | 2022-06-23: 0.5 | 0.5
Continue working for the SpaceType load belong to specific client if data availble for that. | Inventory test site and Api server | 2022-06-23: 3.5 | 3.5
0
0
0
Continue working for the SpaceType load belong to specific client if data availble for that. | Inventory test site and Api server | 2022-06-24: 8 | 8
0
0
0
0
|  | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25 | 40
Approved By: