## Hours Details
Client: |  | System Source |  |  |  |  | Week Ending: |  | 2022-11-19
|  | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Total
Task Descriptions | Subject Area | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19
Continue working to map Donation and Recycle location in Building Drop Down. | Inventory Api & Site | 2022-11-14: 4 | 4
Deploy and testing the changes for the aws s3 bucket changes order flow chaange and Donation and Recycle building drop down changes. | Inventory Api & Site | 2022-11-14: 4 | 4
0
Meeting Call to discuss upcoming changes. | Programmer Meeting call. | 2022-11-15: 2.5 | 2.5
Start working for the Warranty Flow changes to map with Order and Order Items. |  | 2022-11-15: 5.5 | 5.5
0
0
0
Continue working for the Warranty Flow changes to map with Order and Order Items. | Inventory Api & Site | 2022-11-16: 8 | 8
0
0
0
0
Start Testing and fixing the issue while testing for the Warranty flow changes. | Inventory Api & Site | 2022-11-17: 5 | 5
Meeting call | IT Integration | 2022-11-17: 0.5 | 0.5
Fix the issue while testing find issue to map the s3 bucket download image. | Inventory Api & Site | 2022-11-17: 2.5 | 2.5
0
0
0
0
continue working for the Warranty flow to test and fix issue. | Inventory Api & Site | 2022-11-18: 6 | 6
Start looking for the Haworth Api Call. | Haworth Api Call analysis | 2022-11-18: 2 | 2
0
0
0
|  | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 40
Approved By: